## Sheet1
Cincinnati Opioid Research - Capstone Project Initial Work Breakdown Structure
| Week of: | 2020-01-20 | 2020-01-27 | 2020-02-03 | 2020-02-10 | 2020-02-17 | 2020-02-24 | 2020-03-02 | 2020-03-09 | 2020-03-16 | 2020-03-23 | 2020-03-30 | 2020-04-06 | 2020-04-13 | 2020-04-23
| Capstone Deliverables | Initial WBS (Due 1/21) | PP (Due 1/28) | PU1 (Due 2/4) |  |  |  | PU2 (Due 3/4) |  |  | PU3 (Due 3/28) |  |  | FP (Due 4/17) | FR (Due 4/24)
| Work Plan | Phase 1 |  | Hypothesis Testing
|  |  |  | Phase 2 |  | All Preliminary Data Collected
Phase 3
[6 empty] | run rapid hypotheses (pt. 2) |  |  |  |  | Phase 4
Phase 5
Phase 6
| Work Plan Details | [6 empty] | Accountable
| Phase 1 | Literature Review - Research Question and Hypothesis Development *Research Opioid usage in Cincinnati to identify broad themes of the city's drug policy and unique characteristics *Use contextual research and review of prior findings to identify social science theory and/or policy relevant issue to Cincinnati (per SBP-BRiMS guideline) to develop deductive research question *Form initial hypotheses from literature review on what socio-demographic and spatial predictors maybe correlated with high likelihood of opioid use in a given area AND/OR what populations may be most at risk, AND/OR which interventions may be most effective to treat opioid use | [5 empty] | All | 1/17 group did phone call to outline WBS and catch up on plan | 1/23 group phone call. Discuss literature found and setup plan for proposal | 2/4 group phone call. Discussed rapid testing done on EMS in Cincinnati and in Tempe and on the PNML. Also began pulling new data from the ARCOS database. | Hypotheses Tested:
| Phase 2 | Data search, cleaning and structuring *Collect supplementary data to CFD EMS calls based on phase 1 findings *Clean data and merge/re-sample to appropriate spatial-temporal units *Prove validity and reliability of data sources *Push master dataset to be used in all analyses *Generate descriptive statistics *Propose initial research design plan *Conduct Power Analysis and Determine Error Rate | [5 empty] | TBD - Divide based on progress, expertise
| Phase 3 | Analytical Research and Pilot Analysis *Research/Lit Review of ML/Biostatistics/Quantitative Epidemiology papers relevant to question *Modify design as needed *Develop/experiment with various methods (classification vs regression, supervised vs unsupervised, etc.) *Meet weekly to discuss/compare results and suggest model improvements, training/tuning improvements | [5 empty] | TBD - Divide based on progress, expertise
| Phase 4 | Finalize Results and Analysis *Determine "best models" based off error rate and pertinence to question/social theory *Backtesting, validation, quantification of model limitations *Structure/organize results | [5 empty] | TBD - Divide based on progress, expertise
| Phase 5 | Data Visualization, Interpretation and Presentation *Generate data visualizations to interpret results for audiences *Interpret findings and implications for research question *Develop Presentation of Results for Final Presentation *Tie in "1 page teaser" for SBP-BRiMs presentation | [5 empty] | TBD - Divide based on progress, expertise
| Phase 6 | Write Report/Abstract *Write capstone report *Write 2-6 page abstract for SBP-BRiMs submission *Edit abstract based off capstone grade/feedback - final abstract due 5/17 | [5 empty] | TBD - Divide based on progress, expertise